## Dashboard
KolayXport Turkey: weekly dashboard (Phase 1 → 100 activated users)
Targets come from docs/gtm/turkey-gameplan.md §4.8 (checkpoints W2/W4/W6/W8/W10; weeks in between interpolated). Contacts and partners count themselves from 'Partner pipeline'.
Yellow cells = Merisa types the Friday numbers from /admin/partners (signups, activated, paying). Actual < 80% of target in a week that has ended turns red.
Targets: blue = from the gameplan
Week | Starts | Ends | Contacts target | Contacts actual | Partners signed target | Partners signed actual | Partners active target | Partners active actual | Signups target | Signups actual | Activated target | Activated actual | Paying target | Paying actual | Note
W1 | 2026-10-26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Set-up week: shortlist, freelancer, tracking test
W2 | 2026-11-02 |  | 40 |  | 2 |  | 1 |  | 10 |  | 5 |  | 0
W3 | 2026-11-09 |  | 95 |  | 4 |  | 2 |  | 26 |  | 14 |  | 0
W4 | 2026-11-16 |  | 150 |  | 7 |  | 4 |  | 42 |  | 23 |  | 1 |  | First live demo
W5 | 2026-11-23 |  | 205 |  | 10 |  | 5 |  | 63 |  | 34 |  | 2
W6 | 2026-11-30 |  | 260 |  | 12 |  | 7 |  | 85 |  | 45 |  | 3 |  | GTM/GA4/Meta IDs due 30 Nov
W7 | 2026-12-07 |  | 315 |  | 15 |  | 8 |  | 107 |  | 58 |  | 4
W8 | 2026-12-14 |  | 370 |  | 18 |  | 10 |  | 130 |  | 72 |  | 5 |  | Black Friday content via partners
W9 | 2026-12-21 |  | 425 |  | 20 |  | 11 |  | 152 |  | 83 |  | 7 |  | Holiday weeks: light outreach
W10 | 2026-12-28 |  | 480 |  | 23 |  | 13 |  | 175 |  | 95 |  | 9
W11 | 2027-01-04 |  | 535 |  | 26 |  | 14 |  | 195 |  | 100 |  | 10 |  | Gate review: 100 activated + ≥5 paying + tracking live
W12 | 2027-01-11 |  | 590 |  | 28 |  | 15 |  | 215 |  | 110 |  | 11 |  | Phase 2 (if gate passed): Instagram, then Meta ads ₺15k
W13 | 2027-01-18 |  | 645 |  | 31 |  | 16 |  | 235 |  | 120 |  | 12
Phase 2 gate (turkey-gameplan §4.9)
Activated users ≥ 100
Paying customers ≥ 5
GTM / GA4 / Meta IDs live (task T10)
Cookie panel live
Attribution stored on the user (task T24)
Partner pipeline by status
Shortlisted
Contacted
Replied
Terms sent
Signed
Active
Declined
Opted out
Paused
Bounties pending ₺
Bounties paid ₺
Open tasks overdue
Tasks blocked
Formulas:
Contacts actual = IF([Starts]>TODAY(),"",COUNTIFS('Partner pipeline'!$J5:J404,"<="&[Ends]))
Partners signed actual = IF([Starts]>TODAY(),"",COUNTIFS('Partner pipeline'!$O5:O404,"<="&[Ends]))
Partners active actual = IF([Starts]>TODAY(),"",COUNTIFS('Partner pipeline'!$R5:R404,"<="&[Ends]))

## Tasks
Tasks
Edit any row. Owner / Status / Priority are dropdowns. 'Overdue' fills itself; overdue rows turn red. Add new tasks at the bottom (copy the formula in column J).
ID | Task | Owner | Due | Status | Priority | Link | Depends on | Notes | Overdue?
T01 | Push the local docs commits to GitHub (git push origin main): gameplan, referral spec, pricing v2 | Atilla | 2026-10-20 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md |  | Session pushes are blocked by permissions; docs only
T02 | Share this ERP sheet with Merisa and Ekin | Atilla | 2026-10-21 | Not started | P0 |  | T01 | Import the .xlsx into Google Sheets first
T03 | Confirm Merisa's weekly hours (plan assumes ~20 h) | Atilla | 2026-10-24 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md |  | Ekin = ~15 h/week (decided 19 Oct)
T04 | Phone-verify the YouTube channel (lifts upload cap, makes description links clickable) | Atilla | 2026-10-26 | Not started | P0 | https://studio.youtube.com
T05 | Confirm pricing v2 package prices (Başlangıç / Büyüme / Pro / Kurumsal, Aylık) | Atilla | 2026-10-26 | Done | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md |  | Confirmed 19 Oct 19:48 via command board
T05b | Confirm pricing v2 module prices (finance, arbitrage, photo studio, extra store/orders) | Atilla | 2026-10-31 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md |  | Still a proposal
T06 | Take the 4 accountant questions (seller of record + KDV, partner payout paperwork, deductibility) | Atilla | 2026-10-31 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md |  | pricing-v2 §5. Decides iyzico/PayTR entity
T07 | Accountant answers the 4 questions | Accountant | 2026-11-07 | Waiting | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md | T06
T08 | OK to switch the tutorials Unlisted → Public | Atilla | 2026-11-02 | Not started | P1 | https://studio.youtube.com | T04
T09 | Create the Stripe partner coupon(s) and set STRIPE_PARTNER_COUPON_ID via stdin | Atilla | 2026-11-02 | Not started | P0 | https://dashboard.stripe.com/coupons |  | 20% once on yearly / repeating 3 months on Aylık
T10 | Create GTM container + GA4 + Meta pixel IDs and set them in the Hetzner .env | Atilla | 2026-11-30 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/tracking/README.md |  | Phase 2 gate
T11 | Enable Stripe Global Payouts on the Tamsar, Inc. account | Atilla | 2026-12-20 | Not started | P1 | https://dashboard.stripe.com | T07 | Before the first payout run (5 Jan)
T12 | Follow up Hepsiburada integrator ticket 1-404875606841365 | Atilla | 2026-10-21 | Waiting | P1 |  |  | Planned close 21 Oct (Satıcı Paneli › Destek Kayıtlarım)
T13 | Hire a Bionluk freelancer for list-building (120 groups + 60 X/YouTube) | Merisa | 2026-10-27 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md |  | Budget ₺4–6k; brief in gameplan §4.4
T14 | Shortlist + score 110 FB/Telegram groups and 20 müşavirler in Partner pipeline | Merisa | 2026-10-30 | Not started | P0 |  | T13 | Scoring rubric: gameplan §4.4
T15 | Shortlist + score 50 X accounts and 20 YouTube channels in Partner pipeline | Ekin | 2026-10-30 | Not started | P0
T16 | Week 1: 15 helpful answers in target groups (no links) | Merisa | 2026-10-30 | Not started | P1
T17 | Week 1: 15 helpful X replies on e-ihracat threads | Ekin | 2026-10-30 | Not started | P1
T18 | Manual prod check of referral Stage A: open /?ref=TEST-PARTNER, sign up, see 1 signup in /admin/partners, then delete test data | Merisa | 2026-10-24 | Not started | P0 | https://kolayxport.com/admin/partners |  | With Claude d7; see Tests Q01
T19 | Send the first partner messages (Varyant 5 / 6) | Merisa | 2026-11-02 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md | T09, T18 | Only after tracking is confirmed
T20 | Fact-check the blog posts (2 a week) | Merisa | 2026-11-03 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/seo/content-calendar.md |  | Recurring every Tue/Thu
T21 | First live demo in a partner group (scripted, 30 min) | Merisa | 2026-11-18 | Not started | P1
T22 | Ask the first paying customers for written testimonial consent | Merisa | 2026-12-09 | Not started | P2 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/legal-notes.md
T23 | Phase 2: start Instagram organic (only if the gate passed) | Ekin | 2027-01-11 | Not started | P2 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/calendar-30d.md | Gate
T24 | Referral Stage A (capture, claim, admin report) | Claude: d7 (dev) | 2026-10-19 | Done | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/referral-spec.md |  | Deployed b6ee9895
T25 | Referral Stage B (bounty ledger, /app/ortaklik, Stripe Global Payouts) | Claude: d7 (dev) | 2026-11-07 | In progress | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/referral-spec.md | T09 | Spec §3–6
T26 | Pricing v2 P1: plan keys, yearly limits, modules | Claude: to assign | 2026-11-15 | Not started | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md | T05b (modules only) | Package prices decided; can start
T27 | Pricing v2 P2: iyzico/PayTR yearly checkout with taksit | Claude: to assign | 2026-11-30 | Blocked | P0 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md | T07
T28 | Pricing v2 P4: /fiyatlandirma redesign | Claude: gtm-overhaul | 2026-11-30 | Blocked | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md | T05, T07
T29 | Upload the remaining 8 tutorials | Claude: gtm-overhaul | 2026-10-20 | In progress | P1 | https://studio.youtube.com
T30 | Blog cadence: 2 posts a week from the content calendar | Claude: gtm-overhaul | 2026-11-03 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/seo/content-calendar.md | T20
T31 | Draft the /ortaklik partner-terms page (publish after Stage B + accountant) | Claude: gtm-overhaul | 2026-11-07 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md | T07, T25
T32 | Privacy notice: one line on masked referrals shown to partners | Claude: gtm-overhaul | 2026-11-07 | Not started | P1 | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/referral-spec.md |  | Lawyer-review flag
Formulas:
Overdue? = IF(AND([Due]<>"",[Due]<TODAY(),[Status]<>"Done",[Status]<>"Cancelled"),"OVERDUE","")

## Partner pipeline
Partner pipeline
One row per admin / influencer / müşavir. Type, Channel, Owner, Status, Disclosure are dropdowns. Follow-up dates fill themselves (+4/+9/+16 days); 'Next action' turns amber when a follow-up is due. Signups → Bounty paid: copy from /admin/partners, never estimate.
ID | Name / group | Type | Channel | Link | Audience | Score 0–10 | Owner | Status | Date contacted | Follow-up 1 | Follow-up 2 | Follow-up 3 | Next action | Date signed | Ref code | Promo code | First post date | Post link | Disclosure OK | Signups | Activated | Paying | Bounty pending ₺ | Bounty paid ₺ | Notes
P001 | Etsy ile Gelir | tg_admin | Telegram | https://t.me/etsyilegelir | 13102 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P002 | Etsy Türkiye Grubu | tg_admin | Telegram | https://t.me/etsyturkiyegrubu | 2826 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P003 | Etsy Türkiye Yardımlaşma Grubu | tg_admin | Telegram | https://t.me/etsytr | 1735 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P004 | Ebay dropshipping TÜRKİYE | tg_admin | Telegram | https://t.me/ebaydropshippingturkey | 2352 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P005 | Amazon & eBay Yardımlaşma Grubu | tg_admin | Telegram | https://t.me/eBayveamazon | 579 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P006 | Etsy Türk Satıcıları (Etsy Community forumu) | other | Forum | https://community.etsy.com/forum/etsy-t%C3%BCrk-sat%C4%B1c%C4%B1lar%C4%B1-95/ |  |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P007 | Etsy Türkiye Dijital ve POD | other | Forum | https://community.etsy.com/etsy-turkiye-dijital-ve-pod/ | 80 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P008 | ETSY TÜRKİYE SATIŞ TEKNİKLERİ | fb_admin | Facebook | https://www.facebook.com/groups/438314136353104/ |  |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P009 | etsytr (Facebook) | fb_admin | Facebook | https://facebook.com/etsytr |  |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P010 | Mehmet TEK | youtube | YouTube | https://www.youtube.com/@mehmettek | 200000 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P011 | Tuger Akkaya | youtube | YouTube | https://www.youtube.com/@TugerAkkaya | 662000 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P012 | Canberk Ozturk | youtube | YouTube | https://www.youtube.com/@canberkozturkk | 109000 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P013 | Hacı Mehmet KAYA | youtube | YouTube | https://www.youtube.com/@HaciMehmetKAYA | 35800 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P014 | Muhammet USTA | youtube | YouTube | https://www.youtube.com/@MuhammetUSTA | 26300 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P015 | podbul | youtube | YouTube | https://www.youtube.com/@podbulsocial | 12400 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P016 | Veli Seferli | youtube | YouTube | https://www.youtube.com/@veli.seferli | 9100 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P017 | BRMedya | youtube | YouTube | https://www.youtube.com/@BRMedya | 7910 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P018 | Babal Mali Müşavirlik | musavir | YouTube | https://www.youtube.com/@BabalMaliM%C3%BC%C5%9Favirlik | 4470 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P019 | E-Ticaret Adamı | youtube | YouTube | https://www.youtube.com/@eticaretadami | 2110 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P020 | E-İhracat Akademisi (ShipEntegra) | youtube | YouTube | https://www.youtube.com/@shipentegra | 2760 |  | Ekin | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P021 | E-Aramızda (bülten) | other | Substack | https://gkhantanrverdi.substack.com |  |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
P022 | Sıfırdan Globale (bülten) | other | Substack | https://sifirdanglobale.substack.com | 665 |  | Merisa | Shortlisted | [16 empty] | From docs/gtm/social/communities.csv (verified 2026-10-17). Score before contacting.
Formulas:
Next action = IF(OR([Status]="Contacted",[Status]="Terms sent"),IF(TODAY()>=[Follow-up 3],"Close (step 3)",IF(TODAY()>=[Follow-up 2],"Follow-up 2",IF(TODAY()>=[Follow-up 1],"Follow-up 1",""))),IF([Status]="Shortlisted",IF([Score 0–10]="","Score it",""),""))

## Weekly plan
Weekly plan per person (from turkey-gameplan.md §4.7 and §6)
Read-only plan. Change it here only when the gameplan changes. Merisa ~20 h/week, Ekin ~15 h/week on KolayXport.
Week | Starts | Person | Focus | Targets this week | Key tasks
W1 | 2026-10-26 | Merisa | Set-up | Shortlist 130 scored (110 groups + 20 müşavirler); 15 helpful answers | Hire Bionluk freelancer (T13); score shortlist (T14); test Stage A tracking with d7 (T18). Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W1 | 2026-10-26 | Ekin | Set-up | Shortlist 70 scored (50 X + 20 YouTube); 15 X replies | Score shortlist (T15); collect tutorial clips for Shorts. Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W1 | 2026-10-26 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W2 | 2026-11-02 | Merisa | Outreach starts | 30 contacts; 1–2 partners | First Varyant 5 messages (after T09 + T18). Fact-check 2 blog posts. Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W2 | 2026-11-02 | Ekin | Outreach starts | 10 contacts; 0–1 partner | First Varyant 6 messages. Tutorials go Public (T08). Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W2 | 2026-11-02 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W3 | 2026-11-09 | Merisa | Outreach | 40 contacts; first partner posts | Send ready post drafts to signed partners. Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W3 | 2026-11-09 | Ekin | Outreach | 15 contacts | Clips from public tutorials. Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W3 | 2026-11-09 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W4 | 2026-11-16 | Merisa | Outreach + demo | 40 contacts; 7 partners total; first live demo | Run first live demo in a partner group (T21). Review reply/accept rates. Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W4 | 2026-11-16 | Ekin | Outreach + demo | 15 contacts | Prepare demo screens from the demo account. Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W4 | 2026-11-16 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W5 | 2026-11-23 | Merisa | Black Friday angle | 40 contacts | Partners share Black Friday content (blog #1, #7). Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W5 | 2026-11-23 | Ekin | Black Friday angle | 15 contacts | Black Friday clips. Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W5 | 2026-11-23 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W6 | 2026-11-30 | Merisa | Outreach | 40 contacts; 12 partners total; 45 activated | First trial→paid read. Chase T10 (tracking IDs due 30 Nov). Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W6 | 2026-11-30 | Ekin | Outreach | 15 contacts | Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W6 | 2026-11-30 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W7 | 2026-12-07 | Merisa | Second demo | 40 contacts | Second live demo. Ask first paying customers for testimonial consent (T22). Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W7 | 2026-12-07 | Ekin | Outreach | 15 contacts | Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W7 | 2026-12-07 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W8 | 2026-12-14 | Merisa | Outreach | 40 contacts; 18 partners total; 72 activated | Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W8 | 2026-12-14 | Ekin | Outreach | 15 contacts | Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W8 | 2026-12-14 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W9 | 2026-12-21 | Merisa | Holiday, light | 20 contacts | Focus on onboarding new users. Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W9 | 2026-12-21 | Ekin | Holiday, light | 8 contacts | Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W9 | 2026-12-21 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W10 | 2026-12-28 | Merisa | Holiday, light | 20 contacts; 95 activated | First partner payout run on 5 Jan (dry run first). Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W10 | 2026-12-28 | Ekin | Holiday, light | 8 contacts | Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W10 | 2026-12-28 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W11 | 2027-01-04 | Merisa | Gate review | 100 activated, ≥5 paying | Weekly KPI report = gate report to orchestrator/Atilla. Daily ~4 h Mon–Fri: 5 helpful answers in groups (no links), 8 new admin messages (Varyant 5), follow-ups due, partner questions, check partner posts for #işbirliği.
W11 | 2027-01-04 | Ekin | Gate review | 15 contacts | If gate passed: plan Instagram (T23). Daily ~3 h Mon–Fri: 3 X replies/quotes, 3 new messages (Varyant 6), 2 Shorts/clips a week from tutorials.
W11 | 2027-01-04 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W12 | 2027-01-11 | Merisa | Phase 2 (if gate passed) | Meta ads test ₺15k/month per ads-playbook | Run ads per playbook; partnership intros (ShipEntegra, Paraşüt/QNB).
W12 | 2027-01-11 | Ekin | Phase 2: Instagram | 3 posts/week + reels | Instagram from calendar-30d.md.
W12 | 2027-01-11 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.
W13 | 2027-01-18 | Merisa | Phase 2 | Google Search test ₺3–5k | Valentine's/Mother's Day listing-prep content via partners.
W13 | 2027-01-18 | Ekin | Phase 2: Instagram | 3 posts/week + reels
W13 | 2027-01-18 | Weekly | Mon: pick contacts · Fri: KPI report (Dashboard) to orchestrator |  | Merisa fills Dashboard yellow cells on Friday from /admin/partners.

## Content calendar
Content calendar
Blog rows come from docs/gtm/seo/content-calendar.md (drafted by Claude gtm-overhaul, fact-checked by Merisa). Channel / Owner / Status are dropdowns.
Date | Channel | Title / topic | Primary keyword | Links to | Owner | Fact-check | Status | Published link | Notes
2026-11-03 | Blog | Black Friday ve Cyber Monday 2026: Etsy'de indirimi kârı eritmeden kurmak | etsy black friday indirimi | https://kolayxport.com/cozumler/etsy-satici | Claude: gtm-overhaul | Merisa | Draft
2026-11-05 | Blog | Yılbaşı teslimatı için ABD ve Avrupa'ya son gönderim tarihleri (2026) | yılbaşı yurtdışı kargo son gönderim tarihi | https://kolayxport.com/cozumler/mikro-ihracat-kargo-etgb | Claude: gtm-overhaul | Merisa | Draft
2026-11-10 | Blog | Tatil sezonu ilanı: başlıkta "gift" ve "Christmas" ne zaman yazılır? | etsy hediye ilanı nasıl yazılır | https://kolayxport.com/cozumler/ai-ilan-optimizasyonu | Claude: gtm-overhaul | Merisa | Draft
2026-11-12 | Blog | ABD'ye gönderide DDP mi DDU mu? De minimis sonrası karar rehberi | ddp gönderim | https://kolayxport.com/blog/mikro-ihracat-rehberi-2026 | Claude: gtm-overhaul | Merisa | Draft
2026-11-17 | Blog | HS kodu (GTİP) nasıl bulunur? Yanlış kodun yurt dışı gönderide maliyeti | hs kodu nasıl bulunur | https://kolayxport.com/entegrasyonlar/fedex | Claude: gtm-overhaul | Merisa | Draft
2026-11-19 | Blog | Etsy Ads ve Offsite Ads: sezon öncesi reklam bütçesini kâra göre ayarlamak | etsy reklam nasıl verilir | https://kolayxport.com/blog/etsy-kar-hesaplama | Claude: gtm-overhaul | Merisa | Draft
2026-11-24 | Blog | Black Friday haftası: toplu etiket, toplama listesi ve paketleme fişi | toplu kargo etiketi | https://kolayxport.com/cozumler/mikro-ihracat-kargo-etgb | Claude: gtm-overhaul | Merisa | Draft
2026-11-26 | Blog | eBay'de tatil sezonu: ilan, kargo süresi ve fiyat kontrolü | ebay satış arttırma | https://kolayxport.com/cozumler/ebay-satici | Claude: gtm-overhaul | Merisa | Draft
2026-12-01 | Blog | Cyber Week bitti: pazaryeri bazında gerçek net kârınızı çıkarın | pazaryeri kar marjı hesaplama | https://kolayxport.com/nasil-kullanirim/kar-raporu | Claude: gtm-overhaul | Merisa | Draft
2026-12-03 | Blog | "Teslim edildi ama gelmedi": yurt dışı gönderide kanıt ve önlem | kargo teslim edildi görünüyor ama gelmedi | https://kolayxport.com/entegrasyonlar/ups | Claude: gtm-overhaul | Merisa | Draft
2026-12-08 | Blog | AB'ye satışta 2026 kuralları: €3 gümrük, IOSS ve KDV | ioss türkiye | https://kolayxport.com/blog/mikro-ihracat-rehberi-2026 | Claude: gtm-overhaul | Merisa | Draft
2026-12-10 | Blog | Etsy ürün fotoğrafı: boyut, 20 görsel ve 1 video | etsy ürün fotoğrafı boyutu | https://kolayxport.com/cozumler/ai-ilan-optimizasyonu | Claude: gtm-overhaul | Merisa | Draft
2026-12-15 | Blog | Son gönderim tarihinden sonra: işleme süresi, tatil modu ve alıcı mesajı | etsy tatil modu | https://kolayxport.com/cozumler/etsy-satici | Claude: gtm-overhaul | Merisa | Draft
2026-12-17 | Blog | Etsy ürünlerini eBay'de satmak: kategori, fiyat ve kargo farkları | etsy ürünlerini ebay'de satmak | https://kolayxport.com/nasil-kullanirim/etsy-ilanini-ebaye-kopyalama | Claude: gtm-overhaul | Merisa | Draft
2026-12-22 | Blog | 2026'da Türk Etsy satıcılarının en sık yaşadığı 7 sorun | etsy satıcı sorunları | https://kolayxport.com/cozumler/etsy-satici | Claude: gtm-overhaul | Merisa | Draft
2026-12-24 | Blog | Etsy ödemesi gelmedi: Türkiye'den satıcı için kontrol listesi | etsy ödeme ne zaman hesaba geçer | https://kolayxport.com/blog/etsy-kar-hesaplama | Claude: gtm-overhaul | Merisa | Draft
2026-12-29 | Blog | Yıl sonu SKU düzeni: çok kanallı satışta stok karışıklığını önlemek | sku nasıl oluşturulur | https://kolayxport.com/nasil-kullanirim/stok-senkronu-kurulumu | Claude: gtm-overhaul | Merisa | Draft
2026-12-31 | Blog | 2027 gümrük takvimi: ABD 1 Temmuz 2027, AB 2028 | de minimis nedir | https://kolayxport.com/blog/mikro-ihracat-rehberi-2026 | Claude: gtm-overhaul | Merisa | Draft
2027-01-05 | Blog | Sevgililer Günü 2027 için Etsy takvimi: ne zaman listelemeli, ne zaman göndermeli? | etsy sevgililer günü | https://kolayxport.com/cozumler/etsy-satici | Claude: gtm-overhaul | Merisa | Draft
2027-01-07 | Blog | Sevgililer Günü ürün araştırması: talebi veriyle okumak | etsy de en çok ne satılır | https://kolayxport.com/cozumler/urun-arastirma-arbitraj | Claude: gtm-overhaul | Merisa | Draft
2027-01-12 | Blog | Etsy kişiselleştirme alanı: sipariş hatalarını azaltan ayarlar | etsy kişiselleştirme | https://kolayxport.com/cozumler/etsy-satici | Claude: gtm-overhaul | Merisa | Draft
2027-01-14 | Blog | Mikro ihracatta KDV iadesi: ETGB ve e-Arşiv faturayla adım adım | mikro ihracat kdv iadesi | https://kolayxport.com/blog/mikro-ihracat-rehberi-2026 | Claude: gtm-overhaul | Merisa | Draft
2027-01-19 | Blog | Etsy etiketleri nasıl yazılır: 13 etiket, 20 karakter, tekrar yok | etsy etiket nasıl yazılır | https://kolayxport.com/cozumler/ai-ilan-optimizasyonu | Claude: gtm-overhaul | Merisa | Draft
2027-01-21 | Blog | Trendyol ürününüzü Etsy'ye uyarlamak: Türkçe ilandan İngilizce ilana | trendyol ürünlerini etsy'de satmak | https://kolayxport.com/cozumler/trendyoldan-dunyaya | Claude: gtm-overhaul | Merisa | Draft
2027-01-26 | Blog | eBay'de kargo ve iade ayarları: Türkiye'den gönderen satıcı için | ebay kargo ayarları | https://kolayxport.com/entegrasyonlar/ebay | Claude: gtm-overhaul | Merisa | Draft
2027-01-28 | Blog | Q1 planı: Anneler Günü (UK 7 Mart, ABD 9 Mayıs) için ilan ve stok | etsy anneler günü ürünleri | https://kolayxport.com/cozumler/urun-arastirma-arbitraj | Claude: gtm-overhaul | Merisa | Draft
2026-11-02 | YouTube | Tutorial: etsy-baglama |  | https://kolayxport.com/nasil-kullanirim/etsy-baglama | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: ai-ilan-optimizasyonu |  | https://kolayxport.com/nasil-kullanirim/ai-ilan-optimizasyonu | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: ai-urun-fotografi |  | https://kolayxport.com/nasil-kullanirim/ai-urun-fotografi | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: ai-urun-videosu |  | https://kolayxport.com/nasil-kullanirim/ai-urun-videosu | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: etsy-ilan-olusturma |  | https://kolayxport.com/nasil-kullanirim/etsy-ilan-olusturma | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: ebay-ilan-olusturma |  | https://kolayxport.com/nasil-kullanirim/ebay-ilan-olusturma | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: toplu-duzenleme |  | https://kolayxport.com/nasil-kullanirim/toplu-duzenleme | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: anahtar-kelime-arastirmasi |  | https://kolayxport.com/nasil-kullanirim/anahtar-kelime-arastirmasi | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: arbitraj-taramasi |  | https://kolayxport.com/nasil-kullanirim/arbitraj-taramasi | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: chrome-eklentisi |  | https://kolayxport.com/nasil-kullanirim/chrome-eklentisi | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: etgb-ve-e-arsiv |  | https://kolayxport.com/nasil-kullanirim/etgb-ve-e-arsiv | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: kar-raporu |  | https://kolayxport.com/nasil-kullanirim/kar-raporu | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: mesaj-kutusu-ai-yanit |  | https://kolayxport.com/nasil-kullanirim/mesaj-kutusu-ai-yanit | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: siparisler-ve-etiket |  | https://kolayxport.com/nasil-kullanirim/siparisler-ve-etiket | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link
2026-11-02 | YouTube | Tutorial: stok-senkronu |  | https://kolayxport.com/nasil-kullanirim/stok-senkronu | Claude: gtm-overhaul |  | Scheduled |  | Unlisted now; goes Public after Atilla's OK (T08). Some guide slugs differ; check the link

## Tests QA
Tests / QA
Test on production (kolayxport.com) with a test e-mail, on a phone and a laptop. Never use real customer data or the protected review accounts (review@, play-review@, mcp-review@). Result / Tester are dropdowns.
ID | Feature | Steps | Expected | Device | Result | Tester | Date | Bug / link | Notes
Q01 | Referral Stage A: partner link | 1) Private window → kolayxport.com/?ref=TEST-PARTNER 2) Sign up with a test e-mail 3) Open /admin/partners | Report shows 1 signup for TEST-PARTNER; delete test user + partner after | Laptop | Not run
Q02 | Referral: Google sign-in via partner link | 1) Private window → /?ref=TEST-PARTNER 2) Sign up with Google (test account) 3) /admin/partners | Signup attributed (via 'claim') | Phone | Not run
Q03 | Signup + 14-day trial | 1) /login?mode=signup 2) Sign up 3) Verify e-mail 4) Check plan/trial in settings | Trial shows 14 days; no card asked | Phone | Not run
Q04 | Google / Apple first sign-in | Sign in with a new Google account | Lands in the app (no bounce back to /login; fixed in 1b04d991) | Phone | Not run
Q05 | Cookie panel | 1) Fresh browser → 'Yalnızca zorunlu' 2) DevTools network | No requests to facebook.com / google-analytics.com | Laptop | Not run
Q06 | Connect Etsy | Settings › Connections › Etsy → OAuth | Store connected; listings load | Laptop | Not run
Q07 | Listing doctor (onboarding hook) | Open the weakest listing → Listing doctor → apply one fix → send | SEO score + fixes; change stays draft until 'Gönder' | Laptop | Not run
Q08 | Chrome extension from Web Store | Install from chromewebstore.google.com/detail/fjlfihofjojemlofkfejikgdbjemncba → open an Etsy search | Overlay shows plain-Turkish numbers | Laptop | Not run
Q09 | Founding offer counter | Open /fiyatlandirma | Counter shows; never a hardcoded number in copy | Phone | Not run
Q10 | Partner promo code at checkout | After founding spots are full: checkout with the partner code | Discount applied; signup attributed via 'promo' | Laptop | Not run
Q11 | Tutorials embedded on guides | Open 3 guide pages under /nasil-kullanirim | Video plays; links in description work | Phone | Not run
Q12 | Partner dashboard /app/ortaklik (after Stage B) | Log in as a test partner → /app/ortaklik | Own referrals only, masked; no e-mails | Phone | Not run
Q13 | Payout run dry run (after Stage B) | /admin/partners → payout run without confirm | Lists payable bounties; no money moves | Laptop | Not run
Q14 | Shopify-connected account hides referral/prices | Log in to a Shopify-installed test store account | No /app/ortaklik, no prices or upgrades | Laptop | Not run

## Links
Links
GitHub links need repo access (ask Atilla). Stripe, YouTube Studio and the Hetzner server are Atilla-only.
Category | Name | URL / path | Who uses it | Notes
Plan | Turkey gameplan | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/turkey-gameplan.md | Everyone | Phase 1/2, weekly targets, templates (§4.5)
Plan | Pricing v2 (proposal) | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/pricing-v2.md | Atilla
Plan | Referral build spec | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/referral-spec.md | Claude d7
Plan | GTM handbook (marketing README) | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/README.md | Merisa, Ekin | Claims rules, weekly routine
Plan | Feature inventory (only source for claims) | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/feature-inventory.md | Merisa, Ekin | §4 = never claim
Templates | Outreach messages (Varyant 1–4 + follow-ups) | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/outreach-messages.md | Merisa, Ekin | Partner Varyant 5/6 are in gameplan §4.5
Templates | Social kit + claims cheat sheet | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/README.md | Merisa, Ekin
Templates | 30-day social calendar | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/calendar-30d.md | Ekin | Phase 2 Instagram
Templates | Ads playbook | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/ads-playbook.md | Merisa | Phase 2 only
Templates | Legal notes (İYS, #işbirliği, KVKK) | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/legal-notes.md | Merisa, Ekin
Templates | Communities list | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/social/communities.csv | Merisa, Ekin
Templates | Blog content calendar | https://github.com/bloodyteeths/kolayxport_supa/blob/main/docs/gtm/seo/content-calendar.md | Merisa
App | Admin: partners report | https://kolayxport.com/admin/partners | Atilla, Merisa (admin role) | Signups / activated / paying per partner
App | Partner dashboard (after Stage B) | https://kolayxport.com/app/ortaklik | Partners
App | Pricing page | https://kolayxport.com/fiyatlandirma | Everyone
App | Signup | https://kolayxport.com/login?mode=signup | Everyone
App | Use-case pages (ad/partner landing) | https://kolayxport.com/cozumler | Merisa, Ekin | etsy-satici, ebay-satici, ai-ilan-optimizasyonu, mikro-ihracat-kargo-etgb, trendyoldan-dunyaya, urun-arastirma-arbitraj
App | How-to guides | https://kolayxport.com/nasil-kullanirim | Everyone
App | Health check | https://kolayxport.com/api/health | Atilla
External | Chrome extension (Web Store) | https://chromewebstore.google.com/detail/fjlfihofjojemlofkfejikgdbjemncba | Everyone
External | Extension promo video | https://youtu.be/RtHJlVkvAqg | Merisa, Ekin
External | YouTube Studio | https://studio.youtube.com | Atilla
External | Stripe dashboard (Tamsar, Inc.) | https://dashboard.stripe.com | Atilla | Coupons, promo codes, Global Payouts
External | Reklam Kurulu influencer guide (send to partners) | https://ticaret.gov.tr/haberler/ticaret-bakanligi-sosyal-medya-etkileyicileri-icin-kilavuz-yayimladi | Merisa, Ekin
External | Bionluk (freelancers) | https://bionluk.com | Merisa
External | PraPazar packages (pricing reference) | https://prapazar.com/tr/paketler | Atilla | Checked 2026-10-19

## Decisions log
Decisions log
Append only: new decisions at the bottom, never edit old rows (add a new row that supersedes them).
Date | Decision | Decided by | Source | Supersedes / notes
2026-10-14 | Prices Starter ₺2.499 / Growth ₺4.999 / Pro ₺7.999 a month, 14-day no-card trial, founding 40% off for life for the first 20 | Atilla | memory: pricing strategy | Superseded by pricing v2 (2026-10-19) for Turkey
2026-10-17 | Positioning A + C: 'Yurt dışına satışın tek paneli' + 'Trendyol'dan dünyaya' track; domestic features only as supporting proof | Atilla | docs/gtm/positioning.md
2026-10-19 | No free tier: entry is the 14-day trial + founding offer | Atilla | turkey-gameplan §0
2026-10-19 | GTM cash cap ₺25.000/month; no ad spend until 100 activated users (Phase 1 = referral partners) | Atilla | turkey-gameplan §0, §4.9
2026-10-19 | Merisa and Ekin run marketing; Atilla stays out of day-to-day | Atilla | orchestrator
2026-10-19 | Ekin ~15 h/week on KolayXport (30 h split with the Amazon shop) | Atilla | orchestrator
2026-10-19 | Prices shown '+KDV' with the total at checkout | Orchestrator for Atilla | turkey-gameplan §0 | Accountant to confirm (pricing-v2 §5)
2026-10-19 | Partner code after founding spots: 20% off (first yearly payment / first 3 months of Aylık) | Orchestrator for Atilla | turkey-gameplan §2
2026-10-19 | Pricing v2 model: yearly packages main offer, ONE monthly plan (Aylık) + modules; iyzico/PayTR for taksit | Atilla | docs/gtm/pricing-v2.md | Numbers still a proposal (T05)
2026-10-19 | Partner bounty one-time: 25% of the first yearly payment (30% from the 10th paying referral); ₺1.500 for Aylık after the 2nd payment | Atilla | turkey-gameplan §4.2 | Supersedes 30% recurring for 12 months (same day)
2026-10-19 | Partner dashboard in the app with masked referrals; payouts via Stripe Global Payouts | Atilla | referral-spec §4 | Paying entity depends on accountant (T07)
2026-10-19 | Pricing v2 prices CONFIRMED: Başlangıç ₺29.990, Büyüme ₺54.990, Pro ₺89.990, Kurumsal from ₺149.990 a year; Aylık ₺2.999 a month; all +KDV. Module prices still a proposal; partners quote no prices until checkout exists | Atilla | command board 19 Oct 19:48 (via orchestrator) | Seller of record / KDV still with the accountant
2026-10-19 | Payments collected by Tamsar, Inc. (US) in TRY under its agreement with Modsons | Atilla | pricing-v2 §1 | Proposal: Modsons sells to Turkish customers; open with the accountant
2026-10-19 | Cookie panel is live (since 2026-10-17); only tracking IDs gate Phase 2 measurement | gtm-overhaul (verified) | turkey-gameplan §4.9

## Lists (hidden)
Owners | TaskStatus | Priority | PartnerType | Channel | PartnerStatus | YesNo | ContentChannel | ContentStatus | TestResult | Testers | PartnerOwners
Atilla | Not started | P0 | fb_admin | Facebook | Shortlisted | Yes | Blog | Idea | Not run | Merisa | Merisa
Merisa | In progress | P1 | tg_admin | Telegram | Contacted | No | YouTube | Draft | Pass | Ekin | Ekin
Ekin | Waiting | P2 | x_voice | WhatsApp | Replied |  | Shorts/Reels | In review | Fail | Atilla
Claude: d7 (dev) | Blocked |  | youtube | X | Terms sent |  | Instagram | Scheduled | Blocked | Claude: d7 (dev)
Claude: gtm-overhaul | Done |  | musavir | YouTube | Signed |  | X | Published |  | Claude: gtm-overhaul
Claude: deploy -50 | Cancelled |  | other | Instagram | Active |  | Facebook | Cancelled
Claude: orchestrator |  |  |  | Substack | Declined |  | Telegram
Claude: to assign |  |  |  | Forum | Opted out |  | LinkedIn
Freelancer |  |  |  | Other | Paused
Accountant